## Sheet1
Status
ISB Unit | Rank | Project | Description | Sponsor | Project Manager | Start Date | Finish Date | Value | Work Status | Color | % Complete | Status Comment | As Of Date
SecOps | Mike V | Vancouver Gateway Replacement & Logging Server | Replace end-of-life gateway and add a logging server | Land, Dale | Chen, Chris | 4/1/2020 | 3/31/2021 | New | Requested | New | 40% | Primary and secondary servers upgraded and online. Tertiary server will be upgraded and deployed to Kamloops for intra-datacenter redundancy once when back in the office and have a resource. | 5/28/2020
SecOps | Dale L | Secure Internet Service Firewall Replacement | Replace end-of-life Secure Internet Service "SIS" data centre firewalls | Land, Dale | Chen, Chris | 1/15/2020 | 3/31/2021 | New | Requested | New | 10% | Adv Sol came back with some options. I talked to David Ell on SecOps plan (plean is within their options). He is taking that forward to Adv Sol. | 6/03/2020
Advisory | Ryan B | Cloud Security Guardrails | Deliver required cloud security artefacts (eg. standards, guidelines, templates) | Costello, Don | Horncastle, Brian | 8/6/2019 | 6/31/2020 | Critical | Active | Critical | 10% | Created initial list of risks to review with management on Friday. | 5/28/2020
SecOps | Mike V | Security Infrastructure Modernization (Availability/Upgrades) | Upgrade the Converge Edge (CE) and client infrastructure at Kamloops and Vancouver to provide insight and high availability. | Land, Dale | Chen, Chris | 9/1/2019 | 6/12/2020 | On Track | Active | On Track | 80% | Kamloops device configuration and testing completed. Failing production traffic on 5/31 (beginning at 5am). Once completed and new configuration validated and stable2 wks, Vancouver redundancy will be built. | 5/28/2020
SecOps | Mike V | RTMC Local Operations Centre Project (Min. of Transportation) | Remote Transportation Management Centre Local Operation Centre project is to interconnect three Local Operation Centres to the central RTMC DC,to build the security transit points to regulate the traffic into different zones e.g., sensors. | Land, Dale | Chen, Chris | 4/1/2019 | 3/31/2021 | On Track | Active | On Track | 90% | A 10:30am change window was used to test the LOC connectivity on 5/22, no change since then. | 5/28/2020
SecOps | Mike V | AG Project support (EHS & Secure Courtroom) | Secure courtroom project is an integrated courtroom technology suite facilitates a variety of technologies to communicate and interact with each other within a closed environment or an open environment in a secure and private infrastructure. | Land, Dale | Chen, Chris | 4/1/2018 | 3/31/2021 | On Track | Active | On Track | 10% | EHS on hold due COVID. Secure courtroom with upper management for contract decisions. | 5/28/2020
SecOps | Austin H | Security Analytics Platform Maintenance and Enhancements | This platform provides logging and alerting of security events for OCIO and other subscribed customers | Land, Dale | Chen, Chris | 4/1/2020 | 3/31/2021 | On Track | Active | On Track | 10% | Working on bug fixes, no significant gain on percentage of project completion. | 6/03/2020
SecOps | Mike V | BRO/Zeek Intrusion Detection System | New capability for intrusion detection system (BRO/Zeek) for Data Centre and Vancouver site. | Perkins, Gary | Land, Dale | 10/1/2019 | 3/31/2021 | On Track | On Hold | On Hold | 25% | Low priority – Devices are procured and awaiting configuration once a resource becomes available and back in the office. | 5/28/2020
Advisory | Michael F | Security Roles and Responsibilities Review Project | Ensure common understanding of security roles and responsibilities | Costello, Don | Horncastle, Brian | 3/21/2019 | 9/27/2019 | Critical | Active | Critical | 40% | Further discussions with ministry directors and report is progressing. | 6/03/2020