## Sheet1
Project Intake Form
Project Name | Mobile Device Security Standard Update
Project Objective | Merge and update the Mobile Device Security Standard and the Mobile Computing Security Standard.
Project Sponsor | Gary Perkins
Project Owner | Brian Horncastle
Project Lead | Daniel Surdu
Key Deliverables | 1) Feb 10 – Monday - Draft #1 - final Draft #1 review between Brian and Daniel 2) Feb 11 – Tuesday - Draft #2 - review between Burke and Daniel 3) Feb 13 - Thursday - Draft #3 - send draft to Clive/Sharina/Kristina for review 4) Feb 18 – Tuesday - Draft #3 - review draft #3 with Clive/Sharina/Kristina 5) Feb 20 - Thursday - Draft #4 - send draft #4 to Device Services for review 6) Feb 27 - Thursday - Draft #5-Final - meet with Device Services, Burke, Clive/Sharina/Kristina for finalizing Draft #5 - Final 7) Feb 28 – Friday - Draft #6-Final - final Draft #6 review between Brian and Daniel 8) Mar 2 – Monday - Draft #6-Final - send Draft #6-Final to Don Costello and Gary Perkins for review. Request feedback be returned by end of March 10 – Tuesday. 9) March 11 – Wednesday - Draft #7-Final - send Draft #7 to MISOs and other Stakeholders for larger consultation. Request feedback by March 20 – Friday. 10) March 23-27 - follow up with any stakeholder issues from feedback. 11) March 30 - Monday - End of day - Final Version ready for ASRB.
Key Stakeholders | OCIO Ministries
Potential Issues or Risks | Length of consultation period will depend on feedback received.
Benefits | Reduced foot print of the 2 current standards by streamlining the requirements. Increased clarity by merging the two separate standards.
Status/Background | Work in Progress