## Index Page
Project Communications Plan
Project Information
Information contained in table is for illustration purposes
Purpose of Communications Plan | The Communications Plan outlines communication procedures and stakeholder groups for activities related to the "[project name]" Project.
Champion | John |  | Sponsor |  | Jane
Project Manager / Lean Lead | Doe
Access & Update Procedures
Information Access Procedures |  | The Communication Plan is located on the project SP site.
Communications Update Procedures |  | If required, the Project Manager will update the Communications Plan.
Revision History
Prepared by: | Project Manager
Approved by: | Project Sponsor | Approved? |  | Yes | Approval Date | 2019-10-23
Version | Revision Date | Revision Description
0.1 | 2019-10-11 | initial draft
0.2 | 2019-10-23 | PM made edits during meeting. Sponsor approved version at end of meeting.
EPO Template © 2000 to date Gord Gibben, PMP

## Stakeholder Identification
Project Communications Plan
Stakeholder Identification
Information contained in table is for illustration purposes
Stakeholder Group | Communications Objective | Preferred Medium | Reporting Frequency | Responsibility | Notes
Project Champion | Progress; Escalation | meetings; email | monthly; ad hoc when req'd | Sponsor | status reports monthly (plus ad hoc meetings)
Project Sponsor | Progress; Escalation | meetings; email | weekly; ad hoc when req'd | PM | Status reports monthly
Project Team | Progress; Coordination | meetings; email | Daily; ad hoc when req'd | PM | Status reports monthly.
SMEs | Progress; Coordination | meetings; email | ad hoc when req'd | PM | Status reports monthly
All Staff | Intro/Awareness Results | email (maybe All Staff meeting) | Twice (beginning and end) | Sponsor
Clients | Results | email | Once (at end) | Sponsor / Champion

## Document Distribution
Project Communications Plan
Project Document Distribution
Information contained in table is for illustration purposes
Project Document | Repository Location | Approvals Required | Distribution List | Distribution Schedule | Notes
Communications / Change Management Plan | Project SP Library | Sponsor | PM, Project Team, Sponsor | At start of project
Interview Notes / Synopsis | " " | N/A | PM, Project Team, Sponsor | After phase
Mapping of Current Process | " " | N/A | PM | After creation
Action Plan | " " | Sponsor | PM, Project Team, Sponsor, | After approval
Control Plan | " " | Sponsor | PM, Project Team, Sponsor | After approval
Project Plan | " " | Sponsor | PM, Project Team, Sponsor | After approval
Project Schedule | " " | Sponsor | PM, Project Team, Sponsor | After approval
Project Status Reports | " " | Sponsor | PM, Project Team, Sponsor, workshop participants, champion | monthly | Agree with Monthly at this point
Project Completion Statement | " " | Sponsor | PM, Project Team, Sponsor | At project end

## Meeting Plan
Project Communications Plan
Project Meeting Plan
Information contained in table is for illustration purposes
Meeting Subject | Chair / Lead | Attendees | Meeting Objectives | Frequency | Length | Notes
Project Team Meeting | PM | PM, project Team, Lean Consultants, Sponsor | Status; Issues; Decisions | Weekly | 30 mins
Sponsor Meeting | PM | PM, Sponsor | Status; Escalation | biweekly | as required
Ad Hoc Meetings | TBD | Project Team Members as required | to be determined as required | as required | as required