## Risk Register
Information contained in table is for illustration purposes
Risk Description | Possible Consequences | Likihood | Impact | Risk Ranking | Owner | Mitigation Plan | Notes
Team members may be overallocated, resulting in inability to concentrate on initiative. | Schedule impact. | 1 - Very Unlikely | 3 - moderate | Low |  | - reprioritize work - Extend timelines. - add more resources. - decrease scope
Team members / workshop participants may be ‘voluntold’ to participate. | Decreased buy-in by team members. | 3 - Feasible | 3 - moderate | Medium |  | - clearly explain the benefits of the project. Explain "what's in it for them."
Project team (workshop participants) may not be able to come to consensus on some items. | Slower decision making. Lack of decision entirely. | 1 - Very Unlikely | 3 - moderate | Low
|  | 3 - Feasible | 3 - moderate | Medium
|  | 1 - Very Unlikely | 3 - moderate | Low
|  | 2 - Slight | 3 - moderate | Medium
|  | 4 - Likely | 4 - major | High
|  | 2 - Slight | 3 - moderate | Medium
|  | 2 - Slight | 4 - major | Medium
|  | 1 - Very Unlikely | 3 - moderate | Low
|  | 5 - Very Likely | 3 - moderate | High
Risk Register-[Project Name]
To copy the automated risk ranking(column E); Highlight cell above and drag formating down in to the newly created row. Formating of row C and D automatically copies as rows are added
Note on E3: Risk Ranking is auto-generated

## DataLookup (Do not Delete)
Likelihood of Occurrence |  | Severity of Consequence
| 1 - insignificant | 2 - minor | 3 - moderate | 4 - major | 5 - critical
1 - Very Unlikely | Low | Low | Low | Medium | High
2 - Slight | Low | Low | Medium | Medium | High
3 - Feasible | Low | Medium | Medium | High | High
4 - Likely | Medium | Medium | High | High | Extreme
5 - Very Likely | Medium | Medium | High | Extreme | Extreme