## Sheet1
# | Task Name | Start | Days
1 | Kickoff communication with all Stakeholders on Goals and plan for Malware Visibility
2 | NCCS - Add a router to peer with VICRM999 and Wireless AP to support EOIP traffic from building
3 | Add and configure F5 between VICRM999 and new router
4 | Add and configure test firewall in the middle to simulate malware inspection
5 | Acquire IDIR subordinate certificate from production and import into F5
6 | Configure F5 inspection policy to only inspect Traffic to Internet (Using information from OS Fingerprinting )
7 | Communication with NCCS and Device Services to develop areas we want to test and explore (UC & EOIP, printing, Workstations not in IDIR)
8 | Ensure IDIR root certificate is in place on all but a couple of the test workstations I.e. test what happens when the F5 cert is not trusted
9 | Start routing real workstations in Sec Ops through new path
10 | Conduct tests and monitor
11 | Conduct test with different types of non-IDIR devices
12 | Communicate to building what we will be testing and what they can expect
13 | Conduct test and monitor for 2 weeks
14 | Keep Phase 1 up in Lab?
15 | Ensure default action bypass/intercept is working correctly
16 | Pilot completed
# | Task Name | Start | Days
17 | Expand pilot to test subnet | Tue 18-09-04
18 | F5 Premium Support Test | Thu 18-08-23 | 5
19 | NCCS to assign test subnet
20 | Install F5 into Security Stack (location TBD) active link | Sun 18-09-09 | 7
21 | Configure F5 for Phase 2 test | Wed 18-09-19 | 5
22 | Test the solution for non-IDIR devices (e.g., fetch Root Cert, where/how to fetch) in the test subnet - (maybe go with proxy) | Thu 18-09-27 | 14
23 | Engage stakeholders (e.g., NCCS, Device Management) to test different devices (e.g., workstations, printers, mobile devices, etc.) in the test subnet | Thu 18-09-27 | 14
24 | Explore logging, monitoring and alerting options (e.g. through SIEM) | Tue 18-09-18 | 7
25 | Test performance and ensure that non-inspected traffic has no effect to existing applications | Wed 18-10-17 | 7
26 | Install F5 in the other Internet Stack active link | Sun 18-10-28 | 5
27 | Replicate configuration in Vancouver and ensure expected performance. | Tue 18-10-23 | 7
28 | Communicate results to Stakeholders | Wed 18-10-17 | 1
29 | Prepare Service Bulletin & TIB for Phase 3 | Thu 18-10-18 | 1
30 | Prepare for controlled rollout vector by vector (e.g., web email, storage drives, etc.) | Thu 18-10-18 | 1
31 | RFC/ Publish Service Bulletin & TIB for Phase 3 | Mon 18-11-05 | 14
32 | Break into SSL vector by vector (e.g., webmail) | Sun 18-11-25 | 1
33 | Monitor performance/availability | Mon 18-11-26 | 7
34 | Communicate results | Wed 18-12-05 | 1
35 | TOP 5 Vectors through SSL (repeat the whole process from 5.1 -5.4) - reiteration
36 | Documentation/Lessons learned
37 | Communicate Project Closure to Stakeholders
|  | Tue 18-09-04 | 43347
43439
# | Start | Days
17 | Tue 18-09-04 | 1
18 | Thu 18-08-23 | 5
19 | Thu 18-08-23 | 1
20 | Sun 18-09-09 | 7
21 | Wed 18-09-19 | 5
22 | Thu 18-09-27 | 14
23 | Thu 18-09-27 | 14
24 | Tue 18-09-18 | 7
25 | Wed 18-10-17 | 7
26 | Sun 18-10-28 | 5
27 | Tue 18-10-23 | 7
28 | Wed 18-10-17 | 1
29 | Thu 18-10-18 | 1
30 | Thu 18-10-18 | 1
31 | Mon 18-11-05 | 14
32 | Sun 18-11-25 | 1
33 | Mon 18-11-26 | 7
34 | Wed 18-12-05 | 1
35 | Wed 18-12-06 | 1
36 | Wed 18-12-07 | 1
37 | Wed 18-12-08 | 1